## Sheet1
WBS Level | WBS Code | WBS Name | WBS Description
1 | 1 | Software System Implementation | project management
2 | 1.1 | Build Project Plan | project management
3 | 1.1.1 | Create Statement Of Work | project management
3 | 1.1.2 | Obtain approval of Statement of Work | project management
3 | 1.1.3 | Create Project Plane | project management
3 | 1.1.4 | Review project plan with team | project management
3 | 1.1.5 | Obtain aprroval of project plan | project management
2 | 1.2 | Finalize project plan and definition | project management
3 | 1.2.1 | Define system environment | project management
3 | 1.2.2 | Determine current architechture | project management
3 | 1.2.3 | Assess processes on the server | project management
3 | 1.2.4 | Assess printer hardware | project management
3 | 1.2.5 | Communicate with integrator | project management
2 | 1.3 | Complete architecture draft | project management
3 | 1.3.1 | Conduct session | project management
3 | 1.3.2 | Send out prep packet | project management
3 | 1.3.3 | Conduct pre-interviews | project management
3 | 1.3.4 | Conduct session | project management
3 | 1.3.5 | Prepare draft document | project management
2 | 1.4 | Send out draft and review with key sponsor | project management
3 | 1.4.1 | Determine additional requirements | project management
3 | 1.4.2 | Finalize additional session scope | project management
3 | 1.4.3 | Communicate sessions to necessary attendance | project management
3 | 1.4.4 | Conduct requirements sessions | project management
3 | 1.4.5 | Document system requirements | project management
3 | 1.4.6 | Circulate initial requirements draft | project management
3 | 1.4.7 | Document minutes from sessions | project management
3 | 1.4.8 | Prepare final draft | project management